## Sheet1
2016 GPP Action Items
Task | Owner | Due Date | Status
Remote voting begins January 11 |  | 2016-01-11
RV - unsolicited ballots question to ExCom | Will to ExCom | 2016-12-16 | Done, answer communicated via DPCA-Leadership
RV- Remote ballot design to ExCom for comments, Orlando affadavit text | Tom to Will | 2016-12-16 | Open questions from Alex on automating
RV - Ballot design finished | ExCom | 2016-01-01
RV - Draft formal guide for remote voting | Will | 2016-12-20
RV - Formal guide to CCs, procedures for central | Will draft to Team | 2016-01-01
RV - Setup fax | Will | 2016-01-01
RV - Setup email | Shari | 2016-01-04
Update DA website http://www.democratsabroad.org/global_presidential_primary | ?? | 2016-01-08
Finish & publish list of Voting Centers | ?? | 2016-01-11
RV - Assemble group to handle centrally received ballots |  | 2016-01-10
Guide for Voting Center Managers (VCMs)
Early statement on low-visibility VCs | Will to ExCom | 2015-12-16 | Done, communicated via DPCA-Leadership
Early statement on new members: e.g. ID required? | Tom & Bill | 2016-01-01
Guide - outline of topics | Will & Tom | 2015-12-18
Guide - draft all topics | Tom & Team
Guide - outstanding questions & check Orlando (e.g. electioneering)
Guide - distribute finished VCM |  | 2016-01-31
Early statement on not-quite-VCs (remote voter assistance) | Will draft to Team | 2016-01-09
Voting Centers open March 1
VC - Ballot design: provisional and in-person, with ExCom feedback | Tom, Will | 2016-01-10
VC - Primary-in-a-box: “I Voted” stickers, posters |  | 2016-02-01
VC - Lists of already-voted members to VCMs |  | 2016-02-20
VC - Procedure for processing early returns |  | 2016-02-01
VC - Plan for “First in world” press |  | 2016-02-01
VC - Procedures for early returns on Presidential preference |  | 2016-02-01
VC - Support group for VCMs available March 1-8 |  | 2016-02-15
Press & external comms
Press - Plan with Comms | Jim & Will | 2015-12-18
Specific "Why we sign" and "Two primaries" language to leaders | Will, Jim | 2015-12-20
Press - General language to leaders for social media, member emails | Jim & Will | 2015-12-31
Complete voter FAQ for website with Bob V | Will | 2015-12-20
Monitor incoming CC information | Bill (Will to setup) | 2015-12-15 | Ongoing
Press - check with all CCs to clear security for publishing address | Will to setup | 1/3/2016? | ???
Press - Compose list of Voting Centers |  | 2016-01-04 | Impossible, given need to check security with all CCs
Press - Finish press kit with all deadlines, instructions, etc | Will | 2016-01-04
Request to State Department for publication | Tom | 2016-01-10
Miscellaneous
Respond Robin on leaders' quiz | Will | 2015-12-16
Respond DA-Canada, Americas resolution on evoting | Will | 2015-12-18
Determine content of DA-Canada waiver | Will | 2015-12-25
Recruit Americas member to GPP Team | Will & Katie | 2015-12-30
Counting ballots
Count - Procedures for receiving from all Voting Centers
Count - Team to count (in Prien?)
Count - Eliminating duplicates, non-members
Count - Handling provisionals
Count - Checking totals
Original Task List below
Recruit team member from AP | Katie | 2015-10-12 | Done
Recruit team member from Americas | Will | 2015-10-12 | Restarted
Recruit additional team member | Will | 2015-10-12 | Restarted
Setup location for GPP FAQ's | Will | 2015-10-12 | Done
Decide name of team | Will | 2015-10-12 | Done
Draft email to send to leadership | Will | 2015-10-14 | Katie's email enough?
Finish DSP summary guide | Orlando | 2015-10-15 | Done
Remind RVC's to work on out-of-compliance countries | Katie | 2015-10-17 | Done, ExCom meeting early Nov
Announce GPP team to leadership | Katie | 2015-10-17 | Done
Research if there is a way to charge a candidate filing fee | None | 2015-10-17 | Abandoned
Research if there is a way to vet candidates for ballot e.g. poll results | None | 2015-10-17 | Abandoned
Request Country Committees to submit their voting center plans |  | 2015-10-31
Send RVC's list of 2008 and 2012 voting centers | Shari | 2015-11-01
Present GPP at Town Hall | Will | 2015-11-09 | Done
Present GPP at EMEA Regional Meeting | Will | 2015-11-14 | Done
Finalize process for ballot processing |  | 2015-11-15
Define GPP communication plans with Comms |  | 2015-12-30
Message to leaders about voting in two primaries |  | 2015-12-20
Receive info on voting centers |  | 2015-12-31
Receive filing from candidates to be on ballot |  | 2016-01-04
Evaluate fax number for GPP use |  | 2016-01-01
Setup mailbox for email ballots |  | 2016-01-05
Distribute ballots for remote voting |  | 2016-01-05
Distribute ballots for Voting Centers |  | 2016-01-15
Determine how to deal with non-email members | Will | 2016-01-15
Finalize voting center information |  | 2016-01-15
Send global email to members about GPP ballots |  | 2016-01-16
Send voting center setup kit to all voting centers |  | 2016-01-31
Send voiting center info to all members |  | 2016-01-31
Send email to voting centers on how to process ballots |  | 2016-01-31
Send reminder on ballots and voting centers to all members |  | 2016-02-15
Send email reminder to voting centers about returning ballots |  | 2016-02-29
Count ballots | Katie | 2016-03-15